## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed By
VvPHrvR9Ok2IMZ5guo2ep8kAAtHM | Add farmer feedback | Project commercialization | In progress | Medium | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  |  | false | false
RdlYmAkybESEmbNhzo42SskAC4dU | Add the Subscription plans | Project commercialization | In progress | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 03/18/2026 | false | true
CAnKvNqd40KU7JAHiSqlzMkANYdi | Upload the demo video | CDAP Cloud | In progress | Important | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 03/18/2026 | false | true
sH3GPvHOPUWno3AeYsjnGckAB-PM | Train the model stages ideitification | Modals Training | In progress | Important | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  |  | false | false
-CvtUfLg0kiRakYyoR0qb8kAOjb5 | Start learn and work with how generate algorithm | Modals Training | In progress | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 | 10/01/2025 |  | false | false
za4CjYnD3UeUtJERj3XDGskAEugh | Uploaded the log book - February to March 2026 | CDAP Cloud | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/31/2026 |  | 03/31/2026 | false | false | RODRIGO K.A.A.L it22364074
uNjmAe-Y-UaHpp9hj-3ONskANlkB | Log Book - March | Log Book | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/31/2026 |  | 03/31/2026 | false | false | RODRIGO K.A.A.L it22364074
_-cJn3AxokiP0BEV8_QWtMkAOcNF | Log book - February | Log Book | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/26/2026 |  | 02/28/2026 | false | false | RODRIGO K.A.A.L it22364074
E9nxqJhKeUCdUxCBlvWUzckAMkIJ | Log book - January | Log Book | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/26/2026 |  | 01/30/2026 | false | false | RODRIGO K.A.A.L it22364074
SeLVEzW6Yk6nT3znAzWPIMkAI-SH | Log book - December | Log Book | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/26/2026 |  | 12/30/2025 | false | false | RODRIGO K.A.A.L it22364074
pDehtN-piUydSuGH2b9ePMkALRjR | Log book - November | Log Book | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/26/2026 |  | 11/30/2025 | false | false | RODRIGO K.A.A.L it22364074
lXQv-TzzVk6smAvCNLGi18kAGX_v | Log book - October | Log Book | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/26/2026 |  | 10/30/2025 | false | false | RODRIGO K.A.A.L it22364074
uzxiu2-AeU-86B29199iAskANJvQ | Log book - September | Log Book | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/26/2026 |  | 09/30/2025 | false | false | RODRIGO K.A.A.L it22364074
BAh0BFCp6EqEUktTOt9fS8kAFI7m | Log book - August | Log Book | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/26/2026 |  | 08/29/2025 | false | false | RODRIGO K.A.A.L it22364074
3bAa_0DY_UW-TawH5Tc18ckAG-hx | Day of the Progress Presentation 2 | Progress presentation 02 | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | WIJESINGHE M D C M it22330932 | 03/24/2026 |  | 03/09/2026 | false | false | WIJESINGHE M D C M it22330932
UhQDzll-pEK0g6uN3UTbrskADO0y | Fix some errors in backend | Backend development | Completed | Important | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/24/2026 |  | 02/27/2026 | false | false | WIJESINGHE M D C M it22330932
9VWRtXkHLEyEustsMtouFckAGHDc | Create crop calendar & profitability simulator | Frontend developent | Completed | Important | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/24/2026 | 02/02/2026 | 02/18/2026 | false | false | WIJESINGHE M D C M it22330932
nL5o8fizL0qIX99P5LiGcckAEt7R | Update backend | Backend development | Completed | Medium | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/24/2026 |  | 01/31/2026 | false | false | WIJESINGHE M D C M it22330932
sGnfhkvsL0KsrB79R-C0S8kAIwq8 | Update crop recommender page frontend | Frontend developent | Completed | Medium | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/24/2026 |  | 01/16/2026 | false | false | WIJESINGHE M D C M it22330932
yQ8NZJyuQ0-zC-YnJqgDhckAB-Fi | Create admin panel for the my function | Frontend developent | Completed | Important | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/24/2026 |  | 12/25/2025 | false | false | WIJESINGHE M D C M it22330932
bZXaLZcUK0GZhRG3VHkka8kANwBt | Finalized the crop recommender backend part | Backend development | Completed | Important | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/24/2026 |  | 01/05/2026 | false | false | WIJESINGHE M D C M it22330932
YWXCa2SVr0K8VTrGzFFAackAMj54 | Create crop recommender backend (Location detecting part & soil prediction part) | Backend development | Completed | Important | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/24/2026 | 12/29/2025 | 01/02/2026 | false | false | WIJESINGHE M D C M it22330932
WeKPpDSUc0C1ZEldxOBj5skAFVtN | Create Input planner backend part | Backend development | Completed | Important | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/24/2026 | 12/25/2025 | 01/28/2026 | false | false | WIJESINGHE M D C M it22330932
QF3HwCJo4k6Shlpw5qRzRMkAPv4T | Update my dataset | Data Collection | Completed | Medium | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/24/2026 |  | 12/22/2025 | false | false | WIJESINGHE M D C M it22330932
a3F0V0c3bk-WdisQhSSouskAAJby | New data was find from the Batalagoda Rice Research Institute. | Data Collection | Completed | Important | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/24/2026 |  | 12/19/2025 | false | false | WIJESINGHE M D C M it22330932
I1gv6oJGCUqo1p7VzdSeg8kAAZj1 | Create Crop recommender part | Frontend developent | Completed | Important | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/24/2026 | 12/18/2025 | 12/23/2025 | false | false | WIJESINGHE M D C M it22330932
FnKSce1XF0iZJ20ad736UckAJrE5 | Create Input planner page | Frontend developent | Completed | Important | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/24/2026 |  | 12/10/2025 | false | false | WIJESINGHE M D C M it22330932
2bdJv2lDTEa4pjNoUrTqoskAAoC1 | Design Crop calendar page & Input planner page UI | UI design | Completed | Medium | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/24/2026 |  | 12/05/2025 | false | false | WIJESINGHE M D C M it22330932
QAL3BVXEOkauZPywzHqUpskACd7s | Design UI to crop recommender page & Profitability simulator page | UI design | Completed | Medium | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/24/2026 |  | 12/03/2025 | false | false | WIJESINGHE M D C M it22330932
0sCHTLz7xU2I1YolLOCNxskAOJuk | Collect data for my component | Data Collection | Completed | Important | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/24/2026 |  | 11/24/2025 | false | false | WIJESINGHE M D C M it22330932
xF_GfklsF0C-cbgg6fIhS8kAIZGj | Learn how to train model | Modals Training | Completed | Medium |  | WIJESINGHE M D C M it22330932 | 03/24/2026 |  | 11/13/2025 | false | false | WIJESINGHE M D C M it22330932
16bl5bXP0ESbOyTjsG1Bt8kAKhWI | Train the model for Crop Recommendation | Modals Training | Completed | Important | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/24/2026 |  | 01/01/2026 | false | false | WIJESINGHE M D C M it22330932
rKbnCyPivUyh3ARvxmwHsskANMNM | Presentation day | Proposal Presentation | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | WIJESINGHE M D C M it22330932 | 03/24/2026 |  | 09/08/2025 | false | false | WIJESINGHE M D C M it22330932
2qKvXeFQZEm7ACa1Jc5L0skABnZY | Finalized proposal report | Individual Project Proposal Report | Completed | Important | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/24/2026 |  | 09/19/2025 | false | false | WIJESINGHE M D C M it22330932
8-LXV0P4UEWETXIiFA8EE8kAH_Eg | Create proposal report | Individual Project Proposal Report | Completed | Important | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/24/2026 |  | 08/23/2025 | false | false | WIJESINGHE M D C M it22330932
ProLw73X_0CQvlBAzinxVskAKUnj | Adminpanel herbicides - frontend | Frontend developent | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 02/09/2026 | false | false | RODRIGO K.A.A.L it22364074
izZSDUPBOUKIfilDBf9yV8kAKL2p | Added the Agroshop screen - GPS | Frontend developent | Completed | Important | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 02/20/2026 | false | false | RODRIGO K.A.A.L it22364074
kswxQkB7o0CF94yUboeQd8kAAJBl | Train the model storage_model | Modals Training | Completed | Important | DILAKSHAN K it22339942 | DILAKSHAN K it22339942 | 03/18/2026 |  |  | false | false | DILAKSHAN K it22339942
8QHEzwsoR0Orwj0aGnBvk8kAOL_n | Create postharvest_guardian logic | Backend development | Completed | Important | DILAKSHAN K it22339942 | DILAKSHAN K it22339942 | 03/18/2026 |  | 12/29/2025 | false | false | DILAKSHAN K it22339942
CSH91aONJkiyav8wuSySD8kAKWx- | Create Proposal Report | Proposal Report | Completed | Medium | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 03/18/2026 |  |  | false | false | WIJESINGHE M D C M it22330932
Y_9AYvfOVEm5OOjUn-AdhckAF9hr | Updated homepage | UI design | Completed | Medium | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 02/17/2026 | false | false | RODRIGO K.A.A.L it22364074
9QWdBBsJv0y4-rnZ-KQvCskANZET | Created RegisterHarvest page | Frontend developent | Completed | Important | DILAKSHAN K it22339942 | DILAKSHAN K it22339942 | 03/18/2026 |  | 12/23/2025 | false | false | DILAKSHAN K it22339942
8Dd7AE47K0uSPaSSU2wrbckAFgw3 | Created StorageDashboard -frontend | Frontend developent | Completed | Important | DILAKSHAN K it22339942 | DILAKSHAN K it22339942 | 03/18/2026 |  | 12/18/2025 | false | false | DILAKSHAN K it22339942
nWmblgcyg0yHvKbv3C-xkckADjD4 | Get dataset - log book(Bathalagoda) | Data Collection | Completed | Important | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 11/20/2025 | false | false | RODRIGO K.A.A.L it22364074
_BQIkAYrNEWOR8J-tbTyc8kAP9lb | Created RegisterHarvest page | UI design | Completed | Important | DILAKSHAN K it22339942 | DILAKSHAN K it22339942 | 03/18/2026 |  | 12/08/2025 | false | false | DILAKSHAN K it22339942
5rOSCl0MK0CZoqxwdOXlj8kACvJ3 | Uploaded dataset - drive | Modals Training | Completed | Important | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 12/25/2025 | false | false | RODRIGO K.A.A.L it22364074
lr2ZSLtEAUeAv88UU14_8MkABh0a | Created StorageDashboard page | UI design | Completed | Important | DILAKSHAN K it22339942 | DILAKSHAN K it22339942 | 03/18/2026 |  | 11/28/2025 | false | false | DILAKSHAN K it22339942
rKQiskQZlkyonp9ESvuQ58kAGA1F | Weeds Object detection - frontend | Frontend developent | Completed | Important | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 12/31/2025 | false | false | RODRIGO K.A.A.L it22364074
DMGOQOnUYUWXFAnbMfQG_ckAMzsZ | Supervisor gave us the nessory guidelines | Data Collection | Completed | Important | DILAKSHAN K it22339942 | DILAKSHAN K it22339942 | 03/18/2026 |  | 08/15/2025 | false | false | DILAKSHAN K it22339942
co7Bxn1AqUuBq3b7zXlwhskAPQef | created proposal report | Individual Project Proposal Report | Completed | Important | DILAKSHAN K it22339942 | DILAKSHAN K it22339942 | 03/18/2026 |  | 08/22/2025 | false | false | DILAKSHAN K it22339942
Xfp2rjeb00eBRZSNus8mY8kAHGe1 | Created proposal report | Proposal Report | Completed | Medium | DILAKSHAN K it22339942 | DILAKSHAN K it22339942 | 03/18/2026 |  | 08/07/2025 | false | false | DILAKSHAN K it22339942
FhKbJP1iTEKrB2nLpYl2WMkAMJTm | Updated some features | Topic Assessment Form (TAF) | Completed | Medium | DILAKSHAN K it22339942 | DILAKSHAN K it22339942 | 03/18/2026 |  | 06/24/2025 | false | false | DILAKSHAN K it22339942
Z08nsl_EWUOr3g6WaO80ZMkAMv6u | Uploaded the log book - December 2025 to January 2026 | CDAP Cloud | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 02/17/2026 | false | false | RODRIGO K.A.A.L it22364074
80Q5rdgLY0uN5MM-_z-qHMkANHUf | Summited project proposal report | CDAP Cloud | Completed | Important | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 09/19/2025 | false | false | RODRIGO K.A.A.L it22364074
vatz8sr5CEeX3c0XLjtBMMkAKqPy | submitted ReadMe file | CDAP Cloud | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 01/11/2026 | false | false | RODRIGO K.A.A.L it22364074
jUARGqwdWUyJsCjXIds0AckAJ-TM | submitted PP2 to the cloud | CDAP Cloud | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 03/18/2026 | false | false | RODRIGO K.A.A.L it22364074
kWdZBEkWD0aKJkK_tbpsBskAFyXf | Created app home page and sign in and sign up pages | UI design | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 12/29/2025 | false | false | RODRIGO K.A.A.L it22364074
_JgWsUOpAUm-vN6U1cS0NMkAKgH3 | Updated weeds object detection | Frontend developent | Completed | Important | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 01/19/2026 | false | false | RODRIGO K.A.A.L it22364074
vMtjYChmoUWiAZi5rjsL0ckAK9mF | trained model yolo8s - weeds object detection | Modals Training | Completed | Important | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 01/15/2026 | false | false | RODRIGO K.A.A.L it22364074
YLbZZqbKcUiMERoZmuHeL8kAF3sg | finalized proposal report | Individual Project Proposal Report | Completed | Important | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 08/25/2025 | false | false | RODRIGO K.A.A.L it22364074
REl6SUoXLk2J_YtAFIZZ6ckAAoJ5 | Weeds detection frontend development | Frontend developent | Completed | Important | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 12/18/2025 | false | false | RODRIGO K.A.A.L it22364074
6Roi7t0PyUOvRuuAkaT1f8kAJs7W | Added herbicides screen | Frontend developent | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 12/31/2025 | false | false | RODRIGO K.A.A.L it22364074
v8rHvN1dJUeHyY68vIfqAMkABuDD | Updated some features | UI design | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 12/23/2025 | false | false | RODRIGO K.A.A.L it22364074
X7DKwRqdMkOog945VhP3y8kAMmaX | Created weeds detection UI | UI design | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 12/11/2025 | false | false | RODRIGO K.A.A.L it22364074
mIyNWl_9YkGvpFpUHY6EsskAKA6g | Created proposal report | Proposal Report | Completed | Important | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 08/07/2025 | false | false | RODRIGO K.A.A.L it22364074
GL2Qmd9KI0u3Z_ZFEc511ckAAjQf | Updated some features | Topic Assessment Form (TAF) | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 06/24/2025 | false | false | RODRIGO K.A.A.L it22364074
4NyKtZcZtkKS0f8qGpe0O8kAOGXU | Connected the firebase | Frontend developent | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 12/18/2025 | false | false | RODRIGO K.A.A.L it22364074
7wOnJDee5kKMzg6XfSdEQckAOwuy | Setup backend - FlaskApi | Backend development | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 12/05/2025 | false | false | RODRIGO K.A.A.L it22364074
pg3XgGjutUWNl9yruXxgjskAMcFY | Trained model for stages ideitifcations | Modals Training | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 02/19/2026 | false | false | RODRIGO K.A.A.L it22364074
tLK4Bxrfj0OsIdTbwous1ckAP5PK | trained model for weeds 3 types | Modals Training | Completed | Important | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 02/04/2026 | false | false | RODRIGO K.A.A.L it22364074
auoQ69vijUiWoj14XwPwXckANZ3L | Trained mobileNet2 mode for weeds 2 types detection | Modals Training | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 12/18/2025 | false | false | RODRIGO K.A.A.L it22364074
4WzF2tbV10e0_WRYrZaWvskANbWD | Created git brach - weedsW1 | Git Repository | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 03/19/2026 | false | false | RODRIGO K.A.A.L it22364074
ZQ9CTJ9rMUyZgLF-rFzMHMkABdym | Setup frontend and pushed git repo - react native | Git Repository | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 03/19/2026 | false | false | RODRIGO K.A.A.L it22364074
2ys6cEGUMEi_g-jQVuIIFMkALn2M | Created git repo | Git Repository | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 12/18/2025 | false | false | RODRIGO K.A.A.L it22364074
Ef9ldB4vWkSQDJOg6ugp0MkABFK2 | created proposal report | Individual Project Proposal Report | Completed | Medium | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 08/22/2025 | false | false | RODRIGO K.A.A.L it22364074
7w4ELXTrNESW75kvIkAhVckAPSGG | Supervisor gave us the nessory guidelines | Data Collection | Completed | Important | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 08/15/2025 | false | false | RODRIGO K.A.A.L it22364074
CfxTBSMAzkiSLEuiyctwl8kAKtIo | Collected the data for my research component | Data Collection | Completed | Important | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 03/18/2026 |  | 08/20/2025 | false | false | RODRIGO K.A.A.L it22364074
b70j5cpluEa4K_dX126fMMkACoaI | log book january | Log Book | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  |  | false | false | THAMBUGALA T G H D it22906762
r2xPZ6MlR0WfqGIjzy2t7MkACAbQ | log book December | Log Book | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  |  | false | false | THAMBUGALA T G H D it22906762
66rr3A2zLEOLBZklBrusdskAIQ-4 | log book November | Log Book | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  |  | false | false | THAMBUGALA T G H D it22906762
gTweqQxyhUGFPdlNjVa-1MkAH6n_ | log book Octomber | Log Book | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  |  | false | false | THAMBUGALA T G H D it22906762
uXaXL_2fAkmasuTcMx1MVckAAMLf | Log book September | Log Book | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  |  | false | false | THAMBUGALA T G H D it22906762
YPq_k8vyx0GhgeMvDJRVHMkAPE4i | Log book August | Log Book | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  |  | false | false | THAMBUGALA T G H D it22906762
vksNR8uU30Omuc0d_JH_g8kAAqRg | Research paper for finding more information | Research paper | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 03/26/2026 | false | false | THAMBUGALA T G H D it22906762
7wwKvKi57kSMFoIrbbCS8skAGDUp | UI changes with new features | Frontend developent | Completed | Important | THAMBUGALA T G H D it22906762 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 02/16/2026 | false | false | THAMBUGALA T G H D it22906762
TqYswRgUwU2mMSojdb2pickAO4sn | train model for new features | Modals Training | Completed | Important | THAMBUGALA T G H D it22906762 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 02/10/2026 | false | false | THAMBUGALA T G H D it22906762
rqymNO1whUW27MLbxEvDMckABsta | Adding new features for function | Backend development | Completed | Important | THAMBUGALA T G H D it22906762 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 02/09/2026 | false | false | THAMBUGALA T G H D it22906762
J9TFdllakEuNIk62Agah68kALMcO | Research for information gathering | Research paper | Completed | Important | THAMBUGALA T G H D it22906762 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 02/06/2026 | false | false | THAMBUGALA T G H D it22906762
bODSDH62PEKXOeSl0pyVA8kAMbUz | pest v1 | Git Repository | Completed | Important | THAMBUGALA T G H D it22906762 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 01/10/2026 | false | false | THAMBUGALA T G H D it22906762
Wiu06DyONUWLg28aAEtH5MkANMHr | changes make update through the supervisor advises for data driven report | Research paper | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 01/27/2026 | false | false | THAMBUGALA T G H D it22906762
cq73GIcCFU6Hu1f7m1bqpskAGoIA | Get supervisor's update for data analysis report | Research paper | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 01/25/2026 | false | false | THAMBUGALA T G H D it22906762
Ww5-FExxzUCxIaGqSChm68kAPnbV | Create Data Analysis report | Research paper | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 01/23/2026 | false | false | THAMBUGALA T G H D it22906762
TiI-pk0e60GNF4JsBMHWfckAK3Ep | UI changes | UI design | Completed | Important | THAMBUGALA T G H D it22906762 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 01/20/2026 | false | false | THAMBUGALA T G H D it22906762
1GH9H4sW10a40w7lmd_BrMkAGaMu | Make some changes in models | Modals Training | Completed | Important | THAMBUGALA T G H D it22906762 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 01/18/2026 | false | false | THAMBUGALA T G H D it22906762
Hgz9nbh3yUOIuF8icU908skAHcV- | Meeting with supervisor madem after pp1 | Progress Presentation 1 (PP1) | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 01/12/2026 | false | false | THAMBUGALA T G H D it22906762
90NOk82aWUaCpYELCTyo-MkADCip | Readme file with check and submit | Checklist 01 | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 01/11/2026 | false | false | THAMBUGALA T G H D it22906762
lNNsRRZdoky8Mk2hnI2-uckAEH-0 | Readme File updated | Git Repository | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 01/09/2026 | false | false | THAMBUGALA T G H D it22906762
fDc9LRZo90OkjHyIA64Ft8kANK2v | PP1 presentation | Progress Presentation 1 (PP1) | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 01/07/2026 | false | false | THAMBUGALA T G H D it22906762
w9EAom9uVEOTHO_X-Yq4EckAFPBL | Do changing according to the supervisor advise | Modals Training | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 01/03/2026 | false | false | THAMBUGALA T G H D it22906762
DevtHZEc8Ey2rAhqzbHuhskAPEdU | Meeting with supervisor madem | Modals Training | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 01/02/2026 | false | false | THAMBUGALA T G H D it22906762
Y2656K6f1UyTkge0Vn2TKskAHqEP | Improve UI with models output | Frontend developent | Completed | Important | THAMBUGALA T G H D it22906762 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 12/29/2025 | false | false | THAMBUGALA T G H D it22906762
LYT-xoEMtEGmxUbxMATsy8kAPYP0 | Improve model | Modals Training | Completed | Important | THAMBUGALA T G H D it22906762 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 12/25/2025 | false | false | THAMBUGALA T G H D it22906762
CqZO871k1kKWEtfNi3UtyskANnL7 | Changes data from there given | Data Collection | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 12/22/2025 | false | false | THAMBUGALA T G H D it22906762
bmsVL30k-0-uzpQUnjWn6skAJCWx | Field visit -Bathalagoda | Data Collection | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 12/19/2025 | false | false | THAMBUGALA T G H D it22906762
Al09uKtfHEG3s9HnQccXKskABxCJ | Changes Of the UI design | Frontend developent | Completed | Important | THAMBUGALA T G H D it22906762 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 12/18/2025 | false | false | THAMBUGALA T G H D it22906762
CklLQc_zI06aphy1i6lCsckANldZ | Repository update with dependencies | Git Repository | Completed | Important | THAMBUGALA T G H D it22906762 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 12/15/2025 | false | false | THAMBUGALA T G H D it22906762
clxhc4aDL0exY8VLiGWxt8kAA0vK | Updated the some code changes | Backend development | Completed | Important | THAMBUGALA T G H D it22906762 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 12/12/2025 | false | false | THAMBUGALA T G H D it22906762
faJMonzhJ0moQQUgLkCLockAJxIb | some pest data changes | Data Collection | Completed | Important | THAMBUGALA T G H D it22906762 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 12/10/2025 | false | false | THAMBUGALA T G H D it22906762
_C1FEoPrB0aAc0FcLP01VckAMu9J | model searching and improving for pest function | Modals Training | Completed | Important | THAMBUGALA T G H D it22906762 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 12/06/2025 | false | false | THAMBUGALA T G H D it22906762
wm2qbA9750G_xLWXUK_a68kAIhN5 | search some needed data from some books and internet | Data Collection | Completed | Important | THAMBUGALA T G H D it22906762 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 12/03/2025 | false | false | THAMBUGALA T G H D it22906762
V9TxJFHEWk-kaZNWjqyc2skAGhfT | pp1 prepare meeting | Progress Presentation 1 (PP1) | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 01/06/2026 | false | false | THAMBUGALA T G H D it22906762
AwBd_5O_BkCw-9UQxGR4E8kANleL | Installing related extensions and creating environment | Backend development | Completed | Important | THAMBUGALA T G H D it22906762 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 11/25/2025 | false | false | THAMBUGALA T G H D it22906762
uZ7XVIEmlkSGDEHHfpVUkskALPhA | Finding more related data | Data Collection | Completed | Important | THAMBUGALA T G H D it22906762 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 11/24/2025 | false | false | THAMBUGALA T G H D it22906762
cfAyyhwyukuxFappoHE2XMkAFcTP | Call for get some more data from sources | Data Collection | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 11/20/2025 | false | false | THAMBUGALA T G H D it22906762
vjfKUo1Us06D1CJnCZC158kAAvd9 | Final exam for study | To do | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 | 10/25/2025 | 11/18/2025 | false | false | THAMBUGALA T G H D it22906762
fMr5CUuzCUWFgNWO-poOwskAPLDo | Deciding what languages and db we should used | Backend development | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 10/20/2025 | false | false | THAMBUGALA T G H D it22906762
-O18jblY-0GvCTw5gpQI0ckALt1E | Finding some algorithms Informations | Modals Training | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 10/11/2025 | false | false | THAMBUGALA T G H D it22906762
RLOJHEkijk6BY3n-XnOd_MkAJchp | Discuss about how to divide data | Data Collection | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 | 10/06/2025 |  | false | false | THAMBUGALA T G H D it22906762
lB2Mh-yme0uaqxbfPQZVh8kADNxd | Research paper introduction | Research paper | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 02/28/2026 | false | false | THAMBUGALA T G H D it22906762
4qL2mvAc6EWldzdMqKNsmckAA57D | Getting feedback from proposal presentation | Proposal Presentation | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 09/27/2025 | false | false | THAMBUGALA T G H D it22906762
j_FzS2Dw6U6DtFI-ebMOFMkANcNo | Meeting with supervisor | Data Collection | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 09/27/2025 | false | false | THAMBUGALA T G H D it22906762
rvFUi38qM0qosL_HD_zFIMkAOimt | finalized Individual Proposal reports | Individual Project Proposal Report | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 09/19/2025 | false | false | THAMBUGALA T G H D it22906762
FYu4JvEp_0aD7K0Ys402jMkANTZY | prepare for presentation | Proposal Presentation | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 | 09/04/2025 | 09/08/2025 | false | false | THAMBUGALA T G H D it22906762
M8Yv5fPKOEuxBXgBPA-pYMkALHlz | Prepare for document and for proposal reports | Proposal Report | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 | 07/25/2025 | 08/25/2025 | false | false | THAMBUGALA T G H D it22906762
G2tHqiTp30-wOTmCd4R9AskALn1J | charter submission | Topic Assessment Form (TAF) | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 07/23/2025 | false | false | THAMBUGALA T G H D it22906762
s_8b7IH7X0qh17kypcLsJskACtY8 | charter submission for do changes | Topic Assessment Form (TAF) | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 | 07/16/2025 | 07/23/2025 | false | false | THAMBUGALA T G H D it22906762
s4ZZ2gyM5k6q3ShECYEYR8kAEuTA | CDAP TAF Evaluations | Topic Assessment Form (TAF) | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 07/15/2025 | false | false | THAMBUGALA T G H D it22906762
XRrrZCW2xEm87tnJSyR7qMkAItO9 | Getting more knowledge about reaserch topic | Topic Assessment Form (TAF) | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 | 05/29/2025 | 06/26/2025 | false | false | THAMBUGALA T G H D it22906762
d424OtlUOUKGgVCr85xF3ckADjTb | TAF submission | CDAP Cloud | Completed | Important | THAMBUGALA T G H D it22906762;WIJESINGHE M D C M it22330932;DILAKSHAN K it22339942;RODRIGO K.A.A.L it22364074 | THAMBUGALA T G H D it22906762 | 03/14/2026 |  | 06/26/2025 | false | false | THAMBUGALA T G H D it22906762
2HJygBxOf0qZhV6d0DXvr8kAIqCj | Collect the required data | Topic Assessment Form (TAF) | Completed | Important | WIJESINGHE M D C M it22330932 | WIJESINGHE M D C M it22330932 | 02/22/2026 |  |  | false | false | WIJESINGHE M D C M it22330932
jDb3XNelMUuHqQdBMXNlYckADUAe | Collect the required data | Topic Assessment Form (TAF) | Completed | Important | RODRIGO K.A.A.L it22364074 | RODRIGO K.A.A.L it22364074 | 02/22/2026 |  |  | false | false | RODRIGO K.A.A.L it22364074

## Plan name
Plan name | AgroMindProjectPlan
Plan ID | r9hM1Le78k6SQJ5zSmHihckAAwBL
Date of export | 04/26/2026